## quality records
Record ID | Record Type | Open Date | Department | Quality Problem | Risk Level | Root Cause | Assigned Owner | Due Date | Closure Date | Status | CAPA Required | CAPA Effectiveness | Days to Close | Days Overdue | Overdue Status
DEV-001 | Deviation | 2026-01-05 | Packaging | Line-clearance checklist was not signed before packaging started | Major | Personnel | QA Analyst 1 | 2026-02-04 | 2026-01-28 | Closed | Yes | Effective | 23 | 0 | On Time
DEV-002 | Deviation | 2026-01-09 | Manufacturing | Room temperature exceeded the approved limit for 25 minutes. | Major | Environment | QA Analyst 2 | 2026-02-08 | 2026-02-12 | Closed | Yes | Effective | 34 | 4 | Overdue
DEV-003 | Deviation | 2026-01-14 | Warehouse | Incoming material label was missing the internal lot number. | Minor | Procedure | QA Analyst 3 | 2026-02-13 | 2026-02-05 | Closed | No | Not Applicable | 22 | 0 | On Time
DEV-004 | Deviation | 2026-01-21 | Quality Control | A test result was entered into the worksheet without a second-person verification. | Major | Personnel | QC Supervisor | 2026-02-20 | 2026-03-01 | Closed | Yes | Effective | 39 | 9 | Overdue
DEV-005 | Deviation | 2026-02-03 | Packaging | An obsolete SOP copy was found at the packaging workstation. | Major | Procedure | Document Control | 2026-03-05 | 2026-03-02 | Closed | Yes | Effective | 27 | 0 | On Time
DEV-006 | Deviation | 2026-02-11 | Manufacturing | Mixing time was five minutes shorter than the approved batch instruction. | Critical | Personnel | QA Manager | 2026-03-13 | 2026-03-20 | Closed | Yes | Effective | 37 | 7 | Overdue
DEV-007 | Deviation | 2026-02-18 | Warehouse | A released raw material was stored temporarily in the quarantine area. | Minor | Training | Warehouse Lead | 2026-03-20 | 2026-03-10 | Closed | No | Not Applicable | 20 | 0 | On Time
DEV-008 | Deviation | 2026-03-02 | Engineering | Preventive maintenance was completed two days after its due date. | Major | Equipment | Engineering Lead | 2026-04-01 | 2026-04-08 | Closed | Yes | Effective | 37 | 7 | Overdue
DEV-009 | Deviation | 2026-03-12 | Packaging | Material reconciliation exceeded the approved acceptance range. | Critical | Measurement | QA Manager | 2026-04-11 |  | Under Investigation | Yes | Pending Review |  | 107 | Overdue
DEV-010 | Deviation | 2026-03-25 | Manufacturing | Equipment-cleaning record was missing the operator's date. | Minor | Personnel | QA Analyst 1 | 2026-04-24 | 2026-04-15 | Closed | No | Not Applicable | 21 | 0 | On Time
DEV-011 | Deviation | 2026-04-04 | Quality Control | Balance verification was performed after sample weighing began. | Major | Procedure | QC Supervisor | 2026-05-04 | 2026-05-14 | Closed | Yes | Effective | 40 | 10 | Overdue
DEV-012 | Deviation | 2026-04-18 | Manufacturing | A process parameter was corrected without documenting the reason for the change. | Major | Training | QA Analyst 2 | 2026-05-18 |  | CAPA in Progress | Yes | Pending Review |  | 70 | Overdue
DEV-013 | Deviation | 2026-05-02 | Packaging | Printed packaging components remained on the line after batch completion. | Critical | Procedure | Packaging Lead | 2026-06-01 |  | Pending Approval | Yes | Pending Review |  | 56 | Overdue
DEV-014 | Deviation | 2026-05-20 | Warehouse | Temperature-monitoring data contained a four-hour recording gap. | Major | Equipment | Warehouse Lead | 2026-06-19 | 2026-06-25 | Closed | Yes | Ineffective | 36 | 6 | Overdue
DEV-015 | Deviation | 2026-06-12 | Manufacturing | An operator performed a task before the required training was documented. | Major | Training | QA Analyst 3 | 2026-07-12 |  | Open | Yes | Pending Review |  | 15 | Overdue
CAPA-001 | CAPA | 2026-01-12 | Packaging | Retrain operators and revise the line-clearance verification checklist. | Major | Training | Packaging Lead | 2026-02-26 | 2026-02-22 | Closed | Yes | Effective | 41 | 0 | On Time
CAPA-002 | CAPA | 2026-01-29 | Manufacturing | Install an automated alert for room-temperature excursions. | Major | Environment | Engineering Lead | 2026-03-15 | 2026-03-21 | Closed | Yes | Effective | 51 | 6 | Overdue
CAPA-003 | CAPA | 2026-02-07 | Quality Control | Add mandatory second-person verification to the analytical worksheet. | Major | Procedure | QC Supervisor | 2026-03-24 | 2026-03-18 | Closed | Yes | Effective | 39 | 0 | On Time
CAPA-004 | CAPA | 2026-02-20 | Document Control | Remove uncontrolled SOP copies and introduce a monthly document check. | Major | Procedure | Document Control | 2026-04-06 | 2026-04-03 | Closed | Yes | Effective | 42 | 0 | On Time
CAPA-005 | CAPA | 2026-03-05 | Manufacturing | Update mixing-step verification and retrain production operators. | Critical | Training | Manufacturing Lead | 2026-04-19 | 2026-04-28 | Closed | Yes | Effective | 54 | 9 | Overdue
CAPA-006 | CAPA | 2026-03-28 | Engineering | Revise preventive-maintenance escalation and overdue-notification process. | Major | Procedure | Engineering Lead | 2026-05-12 | 2026-05-30 | Closed | Yes | Ineffective | 63 | 18 | Overdue
CAPA-007 | CAPA | 2026-04-15 | Packaging | Revise reconciliation instructions and require independent verification. | Critical | Measurement | QA Manager | 2026-05-30 |  | CAPA in Progress | Yes | Pending Review |  | 58 | Overdue
CAPA-008 | CAPA | 2026-05-01 | Quality Control | Introduce pre-use balance-verification prompts in the worksheet. | Major | Procedure | QC Supervisor | 2026-06-15 | 2026-06-10 | Closed | Yes | Pending Review | 40 | 0 | On Time
CAPA-009 | CAPA | 2026-05-24 | Warehouse | Replace the temperature data logger and create a backup review procedure. | Major | Equipment | Warehouse Lead | 2026-07-08 |  | Pending Approval | Yes | Pending Review |  | 19 | Overdue
CAPA-010 | CAPA | 2026-06-22 | Manufacturing | Create a system block preventing task assignment before training completion. | Major | Training | Training Coordinator | 2026-08-06 |  | Open | Yes | Pending Review |  | 0 | On Time
CC-001 | Change Control | 2026-01-18 | Warehouse | Qualify a new supplier for primary packaging materials. | Major | Material | Supplier Quality | 2026-03-19 | 2026-03-11 | Closed | No | Not Applicable | 52 | 0 | On Time
CC-002 | Change Control | 2026-02-26 | Manufacturing | Replace the mixing vessel with a new model of equivalent capacity. | Critical | Equipment | Validation Lead | 2026-04-27 | 2026-05-06 | Closed | No | Not Applicable | 69 | 9 | Overdue
CC-003 | Change Control | 2026-03-30 | Document Control | Implement electronic approval for controlled SOP revisions. | Major | Procedure | Document Control | 2026-05-29 | 2026-05-25 | Closed | No | Not Applicable | 56 | 0 | On Time
CC-004 | Change Control | 2026-05-08 | Quality Control | Update the approved analytical worksheet template. | Minor | Procedure | QC Supervisor | 2026-07-07 |  | Pending Approval | No | Not Applicable |  | 20 | Overdue
CC-005 | Change Control | 2026-06-10 | Packaging | Introduce a barcode scanner for printed-component verification. | Major | Equipment | Packaging Lead | 2026-08-09 |  | Open | No | Not Applicable |  | 0 | On Time
AUD-001 | Audit Finding | 2026-01-30 | Warehouse | Two training records were not available during the internal audit. | Major | Training | Training Coordinator | 2026-03-01 | 2026-02-25 | Closed | Yes | Effective | 26 | 0 | On Time
AUD-002 | Audit Finding | 2026-02-14 | Document Control | The master document index did not show the current revision of one SOP. | Minor | Procedure | Document Control | 2026-03-16 | 2026-03-20 | Closed | No | Not Applicable | 34 | 4 | Overdue
AUD-003 | Audit Finding | 2026-03-22 | Manufacturing | Cleaning-log corrections did not consistently include initials and dates. | Major | Training | Manufacturing Lead | 2026-04-21 | 2026-05-02 | Closed | Yes | Effective | 41 | 11 | Overdue
AUD-004 | Audit Finding | 2026-05-15 | Engineering | Calibration status labels were difficult to read on two instruments. | Major | Equipment | Engineering Lead | 2026-06-14 |  | CAPA in Progress | Yes | Pending Review |  | 43 | Overdue
AUD-005 | Audit Finding | 2026-06-25 | Packaging | The area logbook review was not completed within the required timeframe. | Minor | Personnel | Packaging Lead | 2026-07-25 |  | Open | No | Not Applicable |  | 2 | Overdue
CMP-001 | Complaint | 2026-01-25 | Packaging | Customer reported a bottle with a damaged tamper-evident seal. | Critical | Material | Complaint Coordinator | 2026-02-24 | 2026-02-27 | Closed | Yes | Effective | 33 | 3 | Overdue
CMP-002 | Complaint | 2026-02-19 | Packaging | Customer reported an unreadable lot number on the product label. | Major | Equipment | Complaint Coordinator | 2026-03-21 | 2026-03-17 | Closed | Yes | Effective | 26 | 0 | On Time
CMP-003 | Complaint | 2026-04-02 | Warehouse | Customer shipment contained one crushed outer carton. | Minor | Material | Distribution Lead | 2026-05-02 | 2026-04-26 | Closed | No | Not Applicable | 24 | 0 | On Time
CMP-004 | Complaint | 2026-05-28 | Packaging | Customer reported that a pump dispenser did not operate correctly. | Major | Material | Complaint Coordinator | 2026-06-27 |  | Under Investigation | Yes | Pending Review |  | 30 | Overdue
CMP-005 | Complaint | 2026-06-30 | Packaging | Customer reported product leakage inside the shipping carton. | Critical | Material | Complaint Coordinator | 2026-07-30 |  | Open | Yes | Pending Review |  | 0 | On Time